|  | SPRINT 2 PLANNING DOCUMENT Customer Data Extraction Pipeline with Email Rules Intelligence, Contact Role Mapping & Engagement Analytics Email Intelligence Platform |
| --- | --- |

| Version | 3.0 (Final) |
| --- | --- |
| Date | February 11, 2026 |
| Sprint Duration | 2–3 Weeks |
| Depends On | Sprint 1 (Complete) |
| Prepares For | Sprint 3 (AI Enrichment Layer) |

| v2.0 | v3.0: Added Response Time Analytics, Thread Completeness Tracking, Contact Communication Patterns. Full engagement analytics suite. |
| --- | --- |

# Table of Contents

# 1. Executive Summary

## 1.1 Sprint Goal

Build the customer intelligence foundation that transforms raw email data into structured, actionable relationship data. This sprint delivers three interconnected capabilities:

- Customer Data Extraction Pipeline — Deterministic extraction of companies, contacts, and their organizational roles from email data

- Email Rules Intelligence — Sync and normalize email rules from Gmail, Outlook, and archive mailboxes into a unified view that reveals how users organize customer communications

- Contact Role Mapping — Classify contacts by seniority level and functional role to enable targeted campaign strategies

- Engagement Analytics Suite — Response time tracking, thread completeness monitoring, and communication pattern analysis to ensure no customer interaction falls through the cracks

## 1.2 Why These Three Together

|  | Customer Engagement Intelligence The platform’s mission is to identify and increase customer engagement. To do this effectively, you need to know WHO you’re engaging with (contact extraction), WHAT role they play in purchase decisions (role mapping), and HOW the account manager currently organizes communications with them (email rules). Together, these create the targeting intelligence that Sprint 3’s AI layer will amplify. |
| --- | --- |

Email rules are a rich, untapped signal. A rule that auto-labels emails from acme.com as “Key Account” tells you how the account manager values that relationship. A rule that forwards emails from a specific contact to a manager suggests escalation patterns. Sprint 2 captures these signals; Sprint 3’s AI interprets them.

## 1.3 What Changed from v1.0

| Addition | Rationale | Sprint 3 Payoff |
| --- | --- | --- |
| Email Rules Ingestion | Rules reveal how users prioritize/organize customer comms | AI analyzes rules to infer relationship importance and engagement patterns |
| Archive Rules via JSON | MBOX/PST/OLM imports have no API — need manual rule entry | Unified rules view across all mailbox types |
| Contact Role/Designation | Campaign targeting needs to know decision-makers vs. operators | AI enriches roles from signatures, LinkedIn data, email patterns |
| Seniority Classification | C-level vs. manager vs. individual contributor changes strategy | AI-powered engagement scoring weighted by seniority |
| Response Time Analytics | Slow responses = relationship decay. Must measure to improve. | AI predicts churn risk from response time degradation trends |
| Thread Completeness | Unanswered emails are dropped balls — need visibility to close loops | AI auto-prioritizes open threads by urgency and relationship value |
| Communication Patterns | Who initiates? Is it balanced? One-sided comms signal disengagement | AI detects engagement asymmetry and recommends re-engagement |

# 2. Architecture

## 2.1 Updated FastAPI Project Structure

| Path | Responsibility |
| --- | --- |
| app/main.py | FastAPI app, CORS, lifespan events |
| app/config.py | Settings via pydantic-settings (Supabase URL, keys, etc.) |
| app/dependencies.py | Supabase client, JWT auth, current_user dependency |
| app/routers/extraction.py | POST /extract, GET /extract/status |
| app/routers/customers.py | CRUD: companies, contacts, roles |
| app/routers/analytics.py | Engagement analytics endpoints |
| app/routers/rules.py | NEW: Email rules sync, view, JSON import |
| app/routers/config.py | Internal domains, free providers, recognition rules |
| app/services/contact_extractor.py | Parse emails → extract addresses + names |
| app/services/company_resolver.py | Domain → company grouping |
| app/services/email_linker.py | Backfill FKs on emails table |
| app/services/role_classifier.py | NEW: Classify contact seniority + functional role |
| app/services/rules_sync.py | NEW: Gmail API + Graph API rule fetching |
| app/services/rules_normalizer.py | NEW: Normalize Gmail/Outlook/JSON rules to unified format |
| app/services/rules_analyzer.py | NEW: Extract engagement signals from rules |
| app/services/response_time_tracker.py | NEW: Compute response times per contact, company, thread |
| app/services/thread_tracker.py | NEW: Detect open/incomplete threads, dropped conversations |
| app/services/comm_pattern_analyzer.py | NEW: Initiation ratio, bidirectionality, frequency patterns |
| app/services/stats_updater.py | Recompute aggregated stats |
| app/models/schemas.py | Pydantic models (request/response) |
| app/models/rules_schema.py | NEW: Unified rule format, JSON import schema |
| app/models/role_schema.py | NEW: Role/seniority enums and models |
| app/utils/domain_parser.py | Email → domain, normalization |
| app/utils/name_parser.py | Display name → first/last |
| app/utils/title_parser.py | NEW: Job title → seniority + functional role |

# 3. Email Rules Intelligence

## 3.1 The Intelligence Value of Email Rules

Email rules/filters are behavioral signals that reveal how an account manager prioritizes and organizes customer relationships. They are created intentionally and represent learned communication patterns.

| Rule Pattern | Example | Intelligence Signal |
| --- | --- | --- |
| Auto-label by sender domain | Emails from @acme.com → label “Key Account” | Account importance ranking. Customer prioritization hierarchy. |
| Forward to manager | Emails from john@bigcorp.com → forward to boss | High-value contact. Escalation-worthy relationship. |
| Auto-archive/skip inbox | Emails from @vendor.com → skip inbox | Low-priority relationship. Potential disengagement signal. |
| Star/mark important | Subject contains “RFQ” → mark important | Revenue-critical communication patterns. |
| Move to specific folder | From @partner.com → move to “Partnerships” | Relationship classification. Customer segmentation. |
| Auto-reply | Out-of-office or auto-response rules | Communication availability patterns. |

## 3.2 Three Ingestion Channels

### 3.2.1 Gmail Filters (API Sync)

For Gmail LIVE-connected mailboxes, filters are synced via the Gmail API (users.settings.filters.list). The existing gmail_filters table stores the raw filter data. Sprint 2 adds the sync service and the normalization layer.

| Gmail API Field | What It Contains |
| --- | --- |
| criteria.from | Sender email or domain pattern |
| criteria.to | Recipient pattern |
| criteria.subject | Subject line match |
| criteria.query | Full Gmail search query syntax |
| criteria.hasAttachment | Boolean attachment filter |
| action.addLabelIds | Labels to apply (need label name lookup) |
| action.removeLabelIds | Labels to remove (INBOX = skip inbox) |
| action.forward | Forwarding email address |

### 3.2.2 Outlook Rules (Microsoft Graph API Sync)

For Outlook LIVE-connected mailboxes, rules are synced via Microsoft Graph (me/mailFolders/inbox/messageRules). The existing outlook_rules table stores the data. Sprint 2 adds the sync service.

| Graph API Field | What It Contains |
| --- | --- |
| conditions.senderContains | Sender name/email patterns |
| conditions.fromAddresses | Specific sender addresses |
| conditions.subjectContains | Subject line keywords |
| conditions.importance | Message importance level |
| actions.moveToFolder | Target folder ID |
| actions.forwardTo | Forwarding recipients |
| actions.markImportance | Set importance level |
| actions.stopProcessingRules | Rule chain termination |

### 3.2.3 Archive Mailbox Rules (JSON Import)

For file-based mailboxes (MBOX, PST, OLM) there is no API to query rules. Users can manually enter their rules via a JSON import. The platform provides a standardized JSON schema and a UI form for guided entry.

|  | JSON Import Schema The JSON schema is designed to be simple enough for manual entry while flexible enough to capture the key intelligence signals. It uses the same normalized format that Gmail and Outlook rules are converted into. |
| --- | --- |

Example JSON import payload:

{ "mailbox_id": "uuid-here", "source": "manual", "rules": [ { "name": "Key Account - Acme Corp", "conditions": { "from_domains": ["acme.com", "acme.co.uk"], "subject_contains": [], "has_attachment": null }, "actions": { "label": "Key Account", "move_to_folder": null, "mark_important": true, "forward_to": null, "skip_inbox": false }, "is_active": true } ] }

## 3.3 Unified Rules Model

All three sources are normalized into a single unified_email_rules table. This provides a consistent view regardless of source and enables cross-mailbox rule analysis.

### 3.3.1 New Table: unified_email_rules

| Column | Type | Description |
| --- | --- | --- |
| id | UUID PK | Primary key |
| mailbox_id | UUID FK → mailboxes | Which mailbox this rule belongs to |
| client_id | UUID FK → clients | Client context for cross-mailbox analysis |
| source_type | TEXT | gmail_api, outlook_api, json_import, manual |
| source_rule_id | TEXT | Original rule ID from Gmail/Outlook (null for manual) |
| rule_name | TEXT | Human-readable rule name/description |
| is_active | BOOLEAN | Whether rule is currently enabled |
| priority | INTEGER | Rule execution order (lower = higher priority) |
| condition_from_addresses | TEXT[] | Specific sender email addresses |
| condition_from_domains | TEXT[] | Sender domain patterns |
| condition_to_addresses | TEXT[] | Recipient email patterns |
| condition_subject_contains | TEXT[] | Subject keyword matches |
| condition_body_contains | TEXT[] | Body keyword matches |
| condition_has_attachment | BOOLEAN | Attachment presence filter |
| condition_importance | TEXT | Message importance level |
| condition_raw | JSONB | Original conditions (for reference) |
| action_label | TEXT | Label/category to apply |
| action_move_to_folder | TEXT | Target folder path |
| action_forward_to | TEXT[] | Forwarding addresses |
| action_mark_important | BOOLEAN | Mark as important |
| action_mark_read | BOOLEAN | Mark as read |
| action_skip_inbox | BOOLEAN | Skip inbox (archive) |
| action_delete | BOOLEAN | Auto-delete |
| action_raw | JSONB | Original actions (for reference) |
| engagement_signal | TEXT | Derived: high_value, low_priority, escalation, segmentation, neutral |
| matched_company_id | UUID FK | Resolved customer_company (if from_domains matches a known company) |
| matched_contact_id | UUID FK | Resolved customer_contact (if from_addresses matches a known contact) |
| synced_at | TIMESTAMPTZ | When last synced from source |
| created_at | TIMESTAMPTZ | When created in platform |
| updated_at | TIMESTAMPTZ | Last modified |

### 3.3.2 Engagement Signal Derivation

During normalization, each rule is analyzed to derive an engagement_signal. This is a Sprint 2 deterministic classification that Sprint 3’s AI will refine:

| Signal | Detection Logic | Campaign Implication |
| --- | --- | --- |
| high_value | mark_important=true OR label contains “key”/“vip”/“priority” | Prioritize in outreach, personalize messaging |
| escalation | forward_to is set (not the user themselves) | Contact triggers management attention, handle carefully |
| low_priority | skip_inbox=true OR mark_read=true OR action_delete=true | Reduce outreach frequency, risk of disengagement |
| segmentation | move_to_folder is set OR label applied (not importance-related) | User has a mental model for this relationship |
| neutral | No strong signal detected | Standard engagement approach |

## 3.4 Rules View (Frontend)

The Email Rules view provides a unified table showing all rules across mailboxes. This is a read-mostly view with the ability to add manual/JSON rules for archive mailboxes.

| UI Element | Description |
| --- | --- |
| Rules Table | Unified list of all rules. Columns: Rule Name, Source (Gmail/Outlook/Manual), Mailbox, Conditions summary, Actions summary, Engagement Signal badge, Active toggle. |
| Filter Bar | Filter by: source type, mailbox, engagement signal, active/inactive. |
| Import Button | Opens JSON import modal. Validates against schema, shows preview before committing. |
| Manual Add Form | Guided form for adding individual rules. Dropdown for conditions/actions. |
| Sync Button | For live mailboxes: triggers re-sync of rules from Gmail/Outlook API. |
| Rule Detail Panel | Click a rule to see full conditions/actions, matched company/contact, original raw data. |
| Engagement Summary | Card at top showing: X high-value rules, Y escalation rules, Z low-priority rules. Quick health indicator. |

# 4. Contact Role & Designation Mapping

## 4.1 Why Role Matters for Customer Engagement

Not all contacts at a company have equal influence on purchasing decisions. A campaign targeting the CEO requires a fundamentally different approach than one targeting an operations coordinator. Sprint 2 establishes the role classification framework that Sprint 3’s AI will auto-populate from email signatures and communication patterns.

## 4.2 Schema Additions to customer_contacts

The customer_contacts table already has a job_title column. Sprint 2 adds structured classification columns alongside it:

| New Column | Type | Description |
| --- | --- | --- |
| seniority_level | TEXT | Enum: c_level, vp, director, manager, senior, mid, junior, intern, unknown. Hierarchical classification for targeting. |
| functional_role | TEXT | Enum: executive, sales, marketing, operations, finance, engineering, support, procurement, legal, hr, other, unknown. Departmental classification. |
| is_decision_maker | BOOLEAN | Whether this contact has purchasing/approval authority. Derived from seniority + role. |
| is_primary_contact | BOOLEAN | Whether this is the main point of contact at the company. Based on email frequency. |
| role_source | TEXT | How the role was determined: manual, email_signature, ai_enriched, inferred. Tracks data quality. |
| role_confidence | DECIMAL(3,2) | Confidence score 0.00–1.00. Manual = 1.0, signature-parsed = 0.7, inferred = 0.3. |
| department | TEXT | Free-text department name (more specific than functional_role). |
| engagement_score | INTEGER | 0–100 score based on email frequency, recency, response rate. Computed by stats_updater. |

## 4.3 Seniority Level Definitions

| Level | Title Patterns | Campaign Priority | Decision Power |
| --- | --- | --- | --- |
| c_level | CEO, CFO, CTO, COO, CMO, President, Owner, Founder | Highest — Executive outreach | Final approval authority |
| vp | VP, Vice President, SVP, EVP | Very High — Strategic engagement | Budget authority |
| director | Director, Head of, Managing Director | High — Solution-level discussions | Departmental decisions |
| manager | Manager, Supervisor, Team Lead, Coordinator | Medium — Operational alignment | Influence, not authority |
| senior | Senior, Lead, Principal, Staff | Medium — Technical validation | Technical decisions |
| mid | Analyst, Specialist, Associate, Engineer | Standard — Day-to-day contact | Implementation input |
| junior | Junior, Assistant, Trainee, Entry-level | Lower — Relationship building | Minimal |
| intern | Intern, Co-op, Fellow | Lowest — Future relationship | None currently |
| unknown | No title available or unclassifiable | Needs enrichment | Unknown |

## 4.4 Title Parser (Deterministic, Sprint 2)

The title parser is a rule-based utility that extracts seniority_level and functional_role from the job_title string. It runs during contact extraction and whenever a contact’s job_title is updated. Sprint 3’s AI will handle ambiguous cases.

### 4.4.1 Parsing Strategy

- Normalize: lowercase, strip extra whitespace, remove common noise words (“at”, “of”, “in”, “the”)

- Seniority detection: match against keyword lists in priority order (c_level first, then vp, director, etc.)

- Role detection: match against functional keywords (sales, marketing, engineering, etc.)

- Decision-maker flag: auto-set for c_level, vp, director seniority levels

- Confidence: set to 0.7 for signature-extracted titles, 0.5 for email-prefix-inferred, 1.0 for manual entry

### 4.4.2 Where Job Titles Come From (Sprint 2)

| Source | Method | Confidence |
| --- | --- | --- |
| Manual entry | User adds via contact edit UI | 1.0 (highest) |
| Email signature | Parse signature block for title patterns (Sprint 2 basic regex, Sprint 3 AI) | 0.7 |
| Email prefix | john.doe.ceo@company.com → infer CEO | 0.3 (low) |
| CSV/JSON import | Bulk import of contact data with titles | 0.9 |
| AI enrichment | Sprint 3: LLM extracts from signature + email context | 0.8–0.95 |

## 4.5 Company-Level Role Summary

For campaign targeting, a company-level view of contact roles is critical. Sprint 2 adds a computed summary to customer_companies:

| New Column on customer_companies | Type | Description |
| --- | --- | --- |
| contact_count | INTEGER | Total contacts at this company |
| decision_maker_count | INTEGER | Contacts flagged as decision makers |
| primary_contact_id | UUID FK | The primary point of contact (highest engagement score) |
| highest_seniority | TEXT | Highest seniority level among contacts (e.g., c_level) |
| engagement_score | INTEGER | Company-level engagement score (0–100, aggregated from contacts) |
| relationship_status | TEXT | active, cooling, dormant, new. Based on recency + frequency. |

# 5. Engagement Analytics Suite

The engagement analytics suite computes actionable metrics from existing email data — no AI required. These metrics directly address the goal of “closing all loops” and ensuring no customer interaction falls through the cracks.

## 5.1 Response Time Analytics

Response time is the strongest leading indicator of relationship health. A team that responds in 2 hours builds trust; a team that takes 3 days signals disinterest. This module computes response times at every level of the hierarchy.

### 5.1.1 What Gets Measured

| Metric | Calculation | Why It Matters |
| --- | --- | --- |
| First Response Time | Time between inbound email received and first outbound reply in the same thread | The #1 metric for customer satisfaction. Industry benchmark: under 1 hour. |
| Average Response Time | Mean response time across all threads with a contact/company over a period | Tracks overall responsiveness trend. Rising average = early warning. |
| Response Time by Contact | Per-contact response time breakdown | Identifies which contacts are being prioritized vs. neglected. |
| Response Time by Company | Aggregated response time across all contacts at a company | Company-level view for account health assessment. |
| Response Time by Day/Hour | Response time patterns by day of week and hour of day | Identifies team bottlenecks (e.g., slow on Mondays, fast on Wednesdays). |
| SLA Compliance | % of threads responded to within configurable SLA threshold (e.g., 4 hours) | Hard metric for service quality. Reportable KPI for management. |

### 5.1.2 How It Works

Response time calculation uses thread_id to group emails into conversations. For each thread, the service identifies inbound-outbound pairs and computes the time delta. The algorithm:

- Group emails by thread_id, ordered by sent_date ascending

- For each inbound email, find the next outbound email in the same thread

- Calculate the time difference (response_time = outbound.sent_date - inbound.sent_date)

- Exclude auto-replies and system-generated emails (detected via email_categories tags)

- Exclude threads where no response was expected (e.g., outbound-only, newsletters)

- Store per-thread response times for aggregation at contact, company, and team levels

### 5.1.3 New Table: email_response_metrics

| Column | Type | Description |
| --- | --- | --- |
| id | UUID PK | Primary key |
| thread_id | TEXT NOT NULL | Thread identifier |
| mailbox_id | UUID FK | Which mailbox |
| inbound_email_id | UUID FK → emails | The inbound email that triggered the response |
| outbound_email_id | UUID FK → emails | The outbound reply (null if unanswered) |
| customer_contact_id | UUID FK | Who sent the inbound email |
| customer_company_id | UUID FK | Which company |
| inbound_at | TIMESTAMPTZ | When the inbound email was received |
| responded_at | TIMESTAMPTZ | When the outbound reply was sent (null if open) |
| response_time_seconds | INTEGER | Response time in seconds (null if unanswered) |
| is_within_sla | BOOLEAN | Whether response met the configured SLA threshold |
| is_business_hours_only | BOOLEAN | Whether calculation excludes non-business hours |
| status | TEXT | responded, open, no_response_needed |
| created_at | TIMESTAMPTZ | When computed |

## 5.2 Thread Completeness Tracking

An unanswered inbound email is a dropped ball. Thread completeness tracking monitors every conversation thread to ensure nothing falls through the cracks. This is the “close all loops” feature.

### 5.2.1 Thread Status Classification

| Thread Status | Definition | Action Required |
| --- | --- | --- |
| complete | Thread’s last message is outbound, or last inbound was a simple acknowledgment (e.g., “Thanks!”) | None — loop is closed |
| awaiting_reply | Last message is inbound, within SLA window (e.g., < 24 hours) | Monitor — reply expected soon |
| overdue | Last message is inbound, past SLA window but < 7 days | Alert — needs immediate attention |
| dropped | Last message is inbound, > 7 days with no reply | Critical — customer may feel ignored |
| outbound_pending | Last message is outbound, awaiting customer response | Monitor — follow up if no response in X days |
| stale | No activity in 30+ days from either side | Review — is re-engagement needed? |

### 5.2.2 New Table: thread_status

| Column | Type | Description |
| --- | --- | --- |
| id | UUID PK | Primary key |
| thread_id | TEXT NOT NULL | Thread identifier (unique) |
| mailbox_id | UUID FK | Which mailbox |
| customer_company_id | UUID FK | Resolved company |
| customer_contact_id | UUID FK | Primary contact in thread |
| subject | TEXT | Thread subject line |
| status | TEXT | complete, awaiting_reply, overdue, dropped, outbound_pending, stale |
| last_message_direction | TEXT | inbound or outbound |
| last_message_at | TIMESTAMPTZ | When last message was sent |
| last_inbound_at | TIMESTAMPTZ | When last inbound message was received |
| last_outbound_at | TIMESTAMPTZ | When last outbound message was sent |
| message_count | INTEGER | Total messages in thread |
| participant_count | INTEGER | Unique participants |
| open_duration_seconds | INTEGER | How long thread has been in current open state |
| sla_deadline | TIMESTAMPTZ | When response is expected by (based on SLA config) |
| is_flagged | BOOLEAN | Manually flagged for follow-up |
| updated_at | TIMESTAMPTZ | Last status recalculation |

|  | The “Close All Loops” Dashboard View The thread_status table powers a real-time dashboard showing: Open Threads (awaiting reply + overdue + dropped), grouped by company, sorted by urgency. Account managers can see at a glance which conversations need attention. The “dropped” threads are highlighted in red — these are the highest-priority items. Sprint 3 AI will add context (e.g., “This thread discusses a $50K RFQ and has been unanswered for 5 days”). |
| --- | --- |

## 5.3 Contact Communication Pattern Analysis

Communication patterns reveal relationship dynamics. One-sided conversations, declining frequency, and initiative imbalance are all quantifiable signals that predict engagement outcomes.

### 5.3.1 Pattern Metrics

| Metric | Calculation | Intelligence Value |
| --- | --- | --- |
| Initiation Ratio | % of threads started by the contact vs. started by the account manager. 50/50 = balanced. | Low initiation from customer = they’re not reaching out. High initiation from customer = they rely on you (good) or have many issues (investigate). |
| Reply Rate | % of outbound emails that receive a reply. Computed per contact over 90-day windows. | Declining reply rate = losing engagement. Consistent 0% = wrong contact or wrong channel. |
| Frequency Trend | Emails per month over rolling 6-month window, with month-over-month change. | Declining frequency = cooling relationship. Sudden spike = potential issue or opportunity. |
| Conversation Depth | Average messages per thread. More messages = deeper engagement. | Shallow threads (1–2 messages) suggest transactional relationship. Deep threads suggest strategic engagement. |
| Time-to-Respond (Their Side) | How long the contact takes to respond to your emails. | Fast responses from them = engaged. Slow = deprioritizing you. |
| Communication Recency Gap | Days since last interaction, measured separately for inbound and outbound. | Outbound gap > 30d = you’re not reaching out. Inbound gap > 30d = they’re not reaching out. Both > 30d = dormant. |

### 5.3.2 Schema: Additions to customer_contacts

| New Column | Type | Description |
| --- | --- | --- |
| avg_response_time_seconds | INTEGER | Our average response time to this contact (seconds) |
| their_avg_response_time | INTEGER | Their average response time to us (seconds) |
| initiation_ratio | DECIMAL(3,2) | 0.0–1.0 — proportion of threads initiated by contact (0.5 = balanced) |
| reply_rate | DECIMAL(3,2) | 0.0–1.0 — % of our emails that get a reply |
| emails_per_month_avg | DECIMAL(8,2) | Average emails per month over last 6 months |
| frequency_trend | TEXT | increasing, stable, declining, inactive. Based on 3-month trend. |
| avg_thread_depth | DECIMAL(5,2) | Average messages per thread |
| last_inbound_at | TIMESTAMPTZ | Most recent email received from this contact |
| last_outbound_at | TIMESTAMPTZ | Most recent email sent to this contact |
| open_thread_count | INTEGER | Number of threads awaiting our reply |
| dropped_thread_count | INTEGER | Number of threads where we never replied (> 7 days) |

### 5.3.3 Schema: Additions to customer_companies

| New Column | Type | Description |
| --- | --- | --- |
| avg_response_time_seconds | INTEGER | Our average response time to this company (across contacts) |
| sla_compliance_rate | DECIMAL(3,2) | % of threads responded within SLA |
| open_thread_count | INTEGER | Total open threads across all contacts |
| dropped_thread_count | INTEGER | Total dropped threads (critical metric) |
| avg_emails_per_month | DECIMAL(8,2) | Average email volume per month |
| frequency_trend | TEXT | increasing, stable, declining, inactive |
| communication_health | TEXT | excellent, good, needs_attention, critical. Composite of all metrics. |

## 5.4 Updated Engagement Score Formula

The engagement score (0–100) now incorporates the new analytics, making it a comprehensive health indicator:

| Factor | Weight | Calculation |
| --- | --- | --- |
| Email Frequency | 20% | Emails per month in last 90 days, normalized to 0–20 |
| Recency | 15% | Days since last email. <7d = 15, <30d = 12, <90d = 6, >90d = 2, >180d = 0 |
| Response Time (Ours) | 15% | Our avg response time. <1h = 15, <4h = 12, <24h = 8, >24h = 3 |
| Reply Rate (Theirs) | 15% | Their reply rate to our emails. Scaled 0–15 |
| Bidirectionality | 10% | Both inbound and outbound exist? Initiation ratio near 0.5 = max score |
| Thread Completeness | 10% | % of threads in “complete” status. Dropped threads penalize heavily |
| Rule Signal Bonus | 8% | high_value rule = +8, escalation = +6, segmentation = +4, low_priority = -4 |
| Seniority Weight | 7% | c_level/vp contacts weighted higher (engagement with decision-makers matters more) |

## 5.5 Communication Health Score (Company-Level)

The communication_health field on customer_companies is a composite score derived from the engagement analytics:

| Health Level | Criteria | Dashboard Treatment |
| --- | --- | --- |
| excellent | SLA compliance > 90%, no dropped threads, engagement score > 70, frequency stable or increasing | Green badge. Low priority for review. |
| good | SLA compliance > 75%, ≤ 2 dropped threads, engagement score 40–70 | Blue badge. Maintain current engagement. |
| needs_attention | SLA compliance 50–75%, OR 3–5 dropped threads, OR declining frequency | Orange badge. Flag for account manager review. |
| critical | SLA compliance < 50%, OR > 5 dropped threads, OR engagement score < 20, OR dormant > 90 days | Red badge. Immediate action required. |

# 6. Extraction Pipeline Design (Updated)

## 6.1 Updated Pipeline Flow

The pipeline now includes role classification, rule matching, and engagement analytics as new stages:

| # | Phase | Description | Output |
| --- | --- | --- | --- |
| 1 | Validate Prerequisites | Verify mailbox, client link, load config (internal domains, free providers). | Go/No-Go |
| 2 | Collect Addresses | Scan emails: extract sender_email, sender_name, parse recipients/cc JSONB. | Deduplicated address list |
| 3 | Classify Domains | Check each domain: internal → skip, free → flag, otherwise → company domain. | Domain map |
| 4 | Upsert Companies | Create/update customer_companies by domain grouping. | Companies populated |
| 5 | Upsert Contacts | Create/update customer_contacts. Link to company. Parse name. | Contacts populated |
| 6 | Classify Roles (NEW) | For contacts with job_title: run title parser to set seniority, role, decision-maker flag. | Roles classified |
| 7 | Create Rules | Auto-generate domain_match recognition rules per company. | Recognition rules |
| 8 | Link Emails | Batch-update emails: set customer_company_id, customer_contact_id, client_id. | Emails FK’d |
| 9 | Match Email Rules (NEW) | Cross-reference unified_email_rules with resolved companies/contacts. Set matched_company_id, matched_contact_id, engagement_signal. | Rules linked |
| 10 | Compute Response Times (NEW) | For each thread: identify inbound-outbound pairs, calculate response_time_seconds. Populate email_response_metrics. | Response metrics |
| 11 | Evaluate Thread Status (NEW) | For each thread: determine status (complete, awaiting, overdue, dropped). Populate thread_status table. | Thread tracking |
| 12 | Analyze Comm Patterns (NEW) | Per contact/company: compute initiation_ratio, reply_rate, frequency_trend, conversation_depth. | Patterns computed |
| 13 | Update Stats (Enhanced) | Compute email stats + engagement_score + communication_health + relationship_status + role summaries. | Stats complete |

## 6.2 Relationship Status Derivation

| Status | Criteria | Suggested Action |
| --- | --- | --- |
| active | Last contact within 30 days AND engagement score > 40 | Maintain cadence, look for upsell opportunities |
| cooling | Last contact 30–90 days ago OR engagement dropping | Re-engage with targeted outreach, check-in call |
| dormant | Last contact > 90 days ago OR engagement score < 20 | Win-back campaign, review if relationship is salvageable |
| new | First contact within 30 days, fewer than 5 total emails | Nurture sequence, establish relationship |

# 7. API Endpoints (Updated)

## 7.1 Extraction Endpoints

| Method | Endpoint | Description |
| --- | --- | --- |
| POST | /api/v1/extract/{mailbox_id} | Trigger full extraction pipeline (contacts, companies, roles, rules matching). Returns job_id. |
| GET | /api/v1/extract/status/{job_id} | Real-time job progress with per-step breakdown. |
| POST | /api/v1/extract/{mailbox_id}/preview | Dry-run: returns extraction preview without writing. |
| DELETE | /api/v1/extract/{mailbox_id}/reset | Clear all extracted data for re-extraction. |

## 7.2 Email Rules Endpoints (New)

| Method | Endpoint | Description |
| --- | --- | --- |
| POST | /api/v1/rules/sync/{mailbox_id} | Sync rules from Gmail/Outlook API for a live mailbox. Normalizes into unified_email_rules. |
| POST | /api/v1/rules/import | Import rules via JSON payload for archive mailboxes. Validates against schema. |
| GET | /api/v1/rules | List all unified rules (paginated). Filter by mailbox, source, engagement signal, active status. |
| GET | /api/v1/rules/{id} | Get single rule detail with matched company/contact info. |
| PUT | /api/v1/rules/{id} | Update rule metadata (name, active toggle). Does not modify source rule. |
| DELETE | /api/v1/rules/{id} | Delete a manually imported rule. API-synced rules can only be deactivated. |
| POST | /api/v1/rules/manual | Add a single rule via guided form input. |
| GET | /api/v1/rules/summary/{client_id} | Engagement signal summary across all mailboxes for a client. |
| POST | /api/v1/rules/match | Re-run rule-to-company/contact matching after extraction updates. |

## 7.3 Customer Endpoints (Updated)

| Method | Endpoint | Description |
| --- | --- | --- |
| GET | /api/v1/companies | List companies with engagement_score, relationship_status, contact counts. |
| GET | /api/v1/companies/{id} | Company detail: contacts with roles, email stats, matched rules, engagement timeline. |
| PUT | /api/v1/companies/{id} | Update company (name, industry, notes). |
| POST | /api/v1/companies/merge | Merge duplicate companies. Reassign contacts, emails, rules. |
| GET | /api/v1/contacts | List contacts with seniority, role, engagement score. Filter by is_decision_maker. |
| GET | /api/v1/contacts/{id} | Contact detail: role info, email history, matched rules. |
| PUT | /api/v1/contacts/{id} | Update contact including job_title, seniority, role (manual override). |
| PUT | /api/v1/contacts/{id}/role | Update role/designation specifically. Sets role_source=manual, confidence=1.0. |
| POST | /api/v1/contacts/{id}/move | Move contact to different company. |
| GET | /api/v1/contacts/decision-makers/{client_id} | List all decision-makers across companies for a client. Campaign targeting view. |

## 7.4 Analytics Endpoints (Updated)

| Method | Endpoint | Description |
| --- | --- | --- |
| GET | /api/v1/analytics/top-companies | Top companies by engagement score (not just volume). |
| GET | /api/v1/analytics/top-contacts | Top contacts by engagement score. |
| GET | /api/v1/analytics/at-risk | Companies with “cooling” or “dormant” status. Re-engagement candidates. |
| GET | /api/v1/analytics/company/{id}/timeline | Email volume + engagement trend over time. |
| GET | /api/v1/analytics/role-distribution/{client_id} | Seniority distribution across all customer contacts. Campaign planning. |
| GET | /api/v1/analytics/engagement-funnel/{client_id} | Contacts by engagement tier: active/cooling/dormant/new. |
| GET | /api/v1/analytics/rules-insights/{client_id} | Engagement signal distribution from email rules. |
| GET | /api/v1/analytics/domains | Domain summary with classification. |
| GET | /api/v1/analytics/unlinked | Extraction coverage report. |
| GET | /api/v1/analytics/response-times/{client_id} | Response time breakdown by company, contact, and time period. SLA compliance rates. |
| GET | /api/v1/analytics/open-threads/{client_id} | All open/overdue/dropped threads, sorted by urgency. The “Close All Loops” view. |
| GET | /api/v1/analytics/dropped-threads/{client_id} | Specifically dropped threads (critical items). Grouped by company, sortable by duration. |
| GET | /api/v1/analytics/comm-patterns/{client_id} | Communication pattern summary: initiation ratios, reply rates, frequency trends. |
| GET | /api/v1/analytics/communication-health/{client_id} | Company-level communication health overview (excellent/good/needs_attention/critical). |

# 8. Database Migrations Summary

| Migration | Type | Details |
| --- | --- | --- |
| internal_domains | New table | client_id, domain, unique constraint. For excluding own-org emails. |
| free_email_providers | New table | domain PK + seed data (16 providers). |
| extraction_jobs | New table | Progress tracking with per-step counts. |
| unified_email_rules | New table | Normalized rules from Gmail, Outlook, JSON import. 30+ columns including engagement signals. |
| email_response_metrics | New table | Per-thread response time tracking. Links inbound → outbound pairs with timing. |
| thread_status | New table | Thread completeness tracking. Status, last message direction, SLA deadline, open duration. |
| customer_contacts | ALTER TABLE | Add 8 role columns + 11 engagement analytics columns (response times, initiation ratio, reply rate, frequency trend, thread counts, etc.). |
| customer_companies | ALTER TABLE | Add 6 role columns + 7 engagement analytics columns (response time, SLA compliance, open/dropped threads, communication health, etc.). |
| New SQL functions | Functions | 6+ new functions for extraction progress, domain summary, stats updates, email linking, engagement scoring. |
| New indexes | Indexes | Indexes on new columns: seniority_level, functional_role, is_decision_maker, engagement_score, relationship_status. |

# 9. Task Breakdown (Updated)

## Phase 1: Foundation (Days 1–2)

| # | Task | Hours | Priority | Status | Depends |
| --- | --- | --- | --- | --- | --- |
| 1.1 | FastAPI scaffolding + config + deps | 2h | Must Have |  | — |
| 1.2 | Supabase client + JWT auth middleware | 2h | Must Have |  | 1.1 |
| 1.3 | SQL: internal_domains + free_email_providers + seeds | 2h | Must Have |  | — |
| 1.4 | SQL: extraction_jobs table | 1h | Must Have |  | — |
| 1.5 | SQL: unified_email_rules table | 2h | Must Have | New | — |
| 1.6 | SQL: ALTER customer_contacts (role columns) | 1h | Must Have | New | — |
| 1.7 | SQL: ALTER customer_companies (engagement columns) | 1h | Must Have | New | — |
| 1.8 | SQL: email_response_metrics table | 1h | Must Have | New | — |
| 1.9 | SQL: thread_status table | 1h | Must Have | New | — |
| 1.10 | SQL: New functions + indexes | 2h | Must Have |  | 1.3–1.9 |
| 1.11 | Domain parser utility | 2h | Must Have |  | — |
| 1.12 | Name parser utility | 2h | Must Have |  | — |
| 1.13 | Title parser utility (seniority + role) | 3h | Must Have | New | — |
| 1.14 | Unit tests for all parsers | 2h | Should Have |  | 1.11–1.13 |

## Phase 2: Core Extraction Engine (Days 3–6)

| # | Task | Hours | Priority | Status | Depends |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Contact Extractor service | 4h | Must Have |  | 1.9, 1.10 |
| 2.2 | Company Resolver service | 4h | Must Have |  | 2.1 |
| 2.3 | Free provider handling | 2h | Must Have |  | 2.2 |
| 2.4 | Recognition rule auto-generation | 2h | Must Have |  | 2.2 |
| 2.5 | Role Classifier service (title → seniority/role) | 3h | Must Have | New | 1.11 |
| 2.6 | Email Linker service (backfill FKs) | 3h | Must Have |  | 2.2 |
| 2.7 | Engagement Score calculator | 3h | Must Have | New | 2.6 |
| 2.8 | Relationship Status derivation | 2h | Must Have | New | 2.7 |
| 2.9 | Stats Updater (enhanced with roles + engagement) | 3h | Must Have | Changed | 2.5–2.8 |
| 2.10 | Extraction orchestrator (13-step pipeline) | 3h | Must Have |  | All above |
| 2.11 | Progress tracking + error handling | 3h | Must Have |  | 2.10 |
| 2.12 | Integration tests | 3h | Should Have |  | 2.10 |

## Phase 3: Email Rules Intelligence (Days 7–9) — NEW

| # | Task | Hours | Priority | Status | Depends |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Gmail rules sync service (API integration) | 4h | Must Have | New | 1.5 |
| 3.2 | Outlook rules sync service (Graph API) | 4h | Must Have | New | 1.5 |
| 3.3 | Rules normalizer (Gmail/Outlook → unified format) | 4h | Must Have | New | 3.1, 3.2 |
| 3.4 | JSON import validator + parser | 3h | Must Have | New | 1.5 |
| 3.5 | Manual rule entry handler | 2h | Should Have | New | 1.5 |
| 3.6 | Engagement signal derivation logic | 3h | Must Have | New | 3.3 |
| 3.7 | Rule-to-company/contact matching | 3h | Must Have | New | 2.2, 3.3 |
| 3.8 | Rules API endpoints (all 9 endpoints) | 4h | Must Have | New | 3.1–3.7 |
| 3.9 | Rules sync integration tests | 2h | Should Have | New | 3.8 |

## Phase 4: Engagement Analytics Suite (Days 10–12) — NEW

| # | Task | Hours | Priority | Status | Depends |
| --- | --- | --- | --- | --- | --- |
| 4.1 | Response time tracker service (thread pairing logic) | 4h | Must Have | New | 2.6 |
| 4.2 | Business hours calculation utility | 2h | Should Have | New | — |
| 4.3 | Populate email_response_metrics table | 3h | Must Have | New | 4.1 |
| 4.4 | Thread status evaluator service | 4h | Must Have | New | 2.6 |
| 4.5 | SLA configuration support (per client) | 2h | Should Have | New | 4.4 |
| 4.6 | Communication pattern analyzer service | 4h | Must Have | New | 2.6 |
| 4.7 | Frequency trend computation (6-month rolling) | 2h | Must Have | New | 4.6 |
| 4.8 | Communication health score derivation | 2h | Must Have | New | 4.1, 4.4, 4.6 |
| 4.9 | Updated engagement score calculator (8-factor) | 3h | Must Have | Changed | 4.1–4.8 |
| 4.10 | Integration tests for analytics services | 2h | Should Have | New | 4.9 |

## Phase 5: API Endpoints + Analytics (Days 13–15)

| # | Task | Hours | Priority | Status | Depends |
| --- | --- | --- | --- | --- | --- |
| 5.1 | Extraction trigger + status endpoints | 3h | Must Have |  | 2.10 |
| 5.2 | Companies CRUD endpoints | 3h | Must Have |  | — |
| 5.3 | Contacts CRUD + role update endpoints | 3h | Must Have | Changed | — |
| 5.4 | Decision-makers listing endpoint | 2h | Must Have | New | 2.5 |
| 5.5 | Company merge + contact move | 3h | Should Have |  | 5.2, 5.3 |
| 5.6 | Config endpoints (domains, providers, rules) | 3h | Must Have |  | — |
| 5.7 | Top companies/contacts analytics | 2h | Must Have |  | 2.9 |
| 5.8 | At-risk companies endpoint | 2h | Must Have | New | 2.8 |
| 5.9 | Response time analytics endpoints | 3h | Must Have | New | 4.3 |
| 5.10 | Open/dropped threads endpoints | 3h | Must Have | New | 4.4 |
| 5.11 | Communication patterns + health endpoints | 2h | Must Have | New | 4.6, 4.8 |
| 5.12 | Role distribution + engagement funnel | 2h | Should Have | New | 2.5, 2.7 |
| 5.13 | Rules insights analytics | 2h | Should Have | New | 3.6 |
| 5.14 | Timeline + domain + unlinked analytics | 3h | Should Have |  | 2.9 |

## Phase 6: Testing + Deployment (Days 16–17)

| # | Task | Hours | Priority | Status | Depends |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Performance test: 10k+ email mailbox | 3h | Must Have |  | All |
| 6.2 | End-to-end: extraction + rules + analytics + engagement | 3h | Must Have |  | All |
| 6.3 | Edge case handling review | 2h | Must Have |  | All |
| 6.4 | Deploy to Railway | 2h | Must Have |  | All |
| 6.5 | Smoke test on production | 1h | Must Have |  | 6.4 |
| 6.6 | API documentation (auto-gen from FastAPI) | 1h | Nice to Have |  | All |

# 10. Effort Summary

| Phase | Tasks | Hours | Days | New/Changed |
| --- | --- | --- | --- | --- |
| Phase 1: Foundation | 14 | 24h | Days 1–2 | 5 new |
| Phase 2: Core Extraction | 12 | 35h | Days 3–6 | 5 new |
| Phase 3: Email Rules Intelligence | 9 | 29h | Days 7–9 | 9 new |
| Phase 4: Engagement Analytics Suite | 10 | 28h | Days 10–12 | 10 new |
| Phase 5: API + Analytics | 14 | 36h | Days 13–15 | 8 new |
| Phase 6: Testing + Deploy | 6 | 12h | Days 16–17 | — |
| TOTAL | 65 | ~164h | 17 working days | 37 new tasks |

|  | Scope Summary: v1.0 → v3.0 v1.0: 37 tasks / ~83h / 10 days (core extraction only). v2.0: 50 tasks / ~126h / 14 days (added email rules + contact roles). v3.0: 65 tasks / ~164h / 17 working days (~3.5 calendar weeks with buffer). The v3.0 additions (response time tracking, thread completeness, communication patterns) are high-value, low-risk features that use data already available in the emails table. They directly deliver on the “close all loops” goal. |
| --- | --- |

# 11. Sprint 3 AI Handoff

## 11.1 What Sprint 2 Provides

| Sprint 2 Output | Sprint 3 AI Enhancement | Model Suggestion |
| --- | --- | --- |
| customer_companies populated | Industry classification, company size estimation | Claude Haiku / GPT-4o-mini |
| customer_contacts with basic roles | Signature-based title extraction, role refinement | Claude Sonnet / GPT-4o |
| seniority_level (rule-based) | AI confidence scoring, ambiguous title resolution | Claude Haiku / GPT-4o-mini |
| engagement_score (formula) | AI-weighted scoring with behavioral signals | Custom pipeline |
| relationship_status (threshold) | Predictive churn detection, trend forecasting | Time-series + LLM |
| unified_email_rules | Rule pattern analysis, relationship importance inference | Claude Sonnet / GPT-4o |
| engagement_signal (deterministic) | Nuanced signal interpretation, cross-rule patterns | Claude Sonnet / GPT-4o |
| email_enrichment (empty) | Sentiment, tone, summary, entities, escalation | Claude Haiku / GPT-4o-mini |
| Response time metrics | AI predicts churn from response time degradation trends | Time-series ML |
| Thread completeness tracking | AI auto-prioritizes open threads by urgency + revenue impact | Claude Sonnet / GPT-4o |
| Communication patterns | AI detects asymmetry, recommends re-engagement strategies | Custom pipeline |
| Communication health scores | AI-refined health scoring with predictive relationship forecasting | Ensemble model |
| Contact dedup (none) | Embedding-based alias detection | Embeddings + LLM verify |

# 12. Definition of Done (Updated)

| # | Acceptance Criteria | Priority | Status |
| --- | --- | --- | --- |
| 1 | Extraction pipeline populates customer_companies and customer_contacts from email data | Must Have |  |
| 2 | 95%+ of non-system emails have customer_company_id and customer_contact_id backfilled | Must Have |  |
| 3 | Internal domains excluded, free providers grouped under Individual Contacts | Must Have |  |
| 4 | Recognition rules auto-generated for each discovered company domain | Must Have |  |
| 5 | Contacts have seniority_level and functional_role classified from job titles | Must Have | New |
| 6 | Decision-makers flagged (is_decision_maker) based on seniority | Must Have | New |
| 7 | Gmail filters sync to unified_email_rules via API | Must Have | New |
| 8 | Outlook rules sync to unified_email_rules via Graph API | Must Have | New |
| 9 | Archive mailbox rules importable via JSON | Must Have | New |
| 10 | Engagement signals derived from email rules and matched to companies/contacts | Must Have | New |
| 11 | Response times computed per thread, contact, and company | Must Have | New |
| 12 | Thread status tracked (complete/awaiting/overdue/dropped) | Must Have | New |
| 13 | Open/dropped threads visible via API (“close all loops” view) | Must Have | New |
| 14 | Communication patterns computed: initiation ratio, reply rate, frequency trend | Must Have | New |
| 15 | Communication health score derived per company | Must Have | New |
| 16 | Engagement scores computed (8-factor formula) for contacts and companies | Must Have | New |
| 17 | Relationship status (active/cooling/dormant/new) derived for companies | Must Have | New |
| 18 | Company and contact CRUD endpoints functional with role + analytics data | Must Have |  |
| 19 | Response time, open threads, comm patterns analytics endpoints working | Must Have | New |
| 20 | Pipeline handles 10k+ emails without timeout | Must Have |  |
| 21 | Deployed to Railway, smoke-tested | Must Have |  |